Project Proposal

DEPI – Data Analysis Track | Round 5 | Instructor: Eng. Abdelrahman El-Farsy

# Project: Dollar Crisis Analysis Project

Objective: To analyse the movement of the Egyptian Pound against the US dollar, identify the main economic factors behind the dollar crisis, and measure its impact on inflation and the cost of living, then present the findings in an interactive four-page Power BI dashboard that is easy to understand for non-economists.

Description: Full title: The Egyptian Pound’s Journey Against the US Dollar: Causes and Impact. The project explains why the US dollar became scarce and expensive in Egypt and what that meant for prices and households. It compares the official exchange rate with the parallel (black) market rate and studies the main drivers: foreign reserves, trade balance, remittances from Egyptians abroad, tourism and Suez Canal revenue, external debt, foreign investment and central bank interest-rate decisions. Data is collected from official sources (Central Bank of Egypt, CAPMAS, World Bank, IMF), cleaned with Python, queried with light SQL, and visualised in Power BI. Relationships between indicators are reported as associations, not as proven causes.

Tools & Design: Power BI Desktop for a four-page dashboard (Executive Overview, Drivers of the Crisis, Impact on Citizens, Parallel Market & Policy) with a consistent theme, KPI cards, slicers, drill-through and tooltips. Dashboard wireframes are approved by the team before development. A star-schema data model and a data dictionary document the data.

Technologies to Use: Python (pandas, NumPy, Jupyter Notebook) for collection and cleaning; SQL (SQL Server) for data modeling and analytical queries; Power BI Desktop with Power Query and DAX for the dashboard; Excel/CSV for data staging; GitHub for version control.

Team Members & Responsibilities:

- Malak Emad Kamal Soltan – Team Lead & Documentation: planning, task tracking, proposal and final documentation.

- Romysaa Khalid Abdelmajed Asfour – Data Collection: identifies official sources and downloads the raw datasets.

- Malak Ibrahim Abdelmomean Mohammed – Data Cleaning (Python): cleaning, standardisation and derived indicators.

- Radwa Essam Eldin Said Hashkeel – SQL & Data Modeling: database design, ERD and analytical queries.

- Israa El Husseini Mohamed Al Afify – Power BI Developer: dashboard design, data model in Power BI and DAX measures.

- Maryam Mohammad Ebraheem Eldosoky Hegazy – Research & Quality Assurance: economic background, insights, testing and validation.

# Week 1: Planning, Research & Data Collection

- Finalize scope, research questions and the list of indicators (Member 1, all members).

- Study the key economic concepts and prepare a short glossary for the team (Member 6).

- Identify and document official data sources: CBE, CAPMAS, World Bank, IMF (Member 2).

- Download exchange rate, inflation, reserves, trade, remittances and interest-rate data (Members 2, 3).

- Write the Literature Review and Requirements Gathering documents (Members 1, 6).

- Prepare the project plan, roles, risk assessment and KPIs (Member 1).

Deliverables:

- Approved project scope and research questions

- Data source list with links and notes

- Raw datasets folder (unmodified files)

- Literature Review and Requirements Gathering documents

# Week Data Cleaning, Modeling & SQL: [Tasks Description With Team Member Responsibility]

- Inspect raw data for missing values, duplicates and inconsistent dates (Member 3).

- Clean and standardise the data with Python and unify time frequency (Member 3).

- Create derived indicators: monthly % change, official vs parallel gap, real values (Member 3).

- Design the star-schema data model and load the data into SQL Server (Member 4).

- Write light SQL queries: largest monthly jumps, averages before/after devaluations, year-over-year change (Member 4).

- Validate cleaned data against the original source figures (Members 2, 6).

Deliverables:

- Cleaned datasets and Python notebook

- ERD / data model diagram

- SQL scripts with query results

- Data dictionary and validation log

# Week Dashboard Design & Development: [Tasks Description With Team Member Responsibility]

- Create wireframes for the four dashboard pages and get team approval (Member 5).

- Import the data into Power BI, build relationships and DAX measures (Members 5, 4).

- Build Page 1 (Executive Overview) and Page 2 (Drivers of the Crisis) (Member 5).

- Build Page 3 (Impact on Citizens) and Page 4 (Parallel Market & Policy) (Members 5, 3).

- Add slicers, drill-through, tooltips and a consistent theme (Member 5).

- Write key insights and short explanations for each page (Members 6, 1).

Deliverables:

- Approved dashboard wireframes

- Power BI file (.pbix) with four pages

- Documented DAX measures

- Draft insights and recommendations

# Week Testing, Documentation & Final Presentation: [Tasks Description With Team Member Responsibility]

- Check dashboard numbers against source data and SQL results (Members 2, 4, 6).

- Test filters, interactions, performance and readability (Members 5, 3).

- Fix issues and record them in a bug log (Members 5, 3).

- Complete the Project Documentation: analysis & design, test cases, user manual (Members 1, 6).

- Prepare the final presentation and an optional short demo video (Members 1, 5).

- Upload all files to GitHub and submit the final deliverables (all members).

Deliverables:

- Final .pbix file and PDF export of the dashboard

- Test cases and bug report

- Final documentation and user manual

- Final presentation (PPT/PDF)